## TrackingSystem
Module | Task | Description | Status | Comment
Customer | Add new customer | Create a post service to save new customer details to db Input fields – Customer details | done
| Customer validations | Validation: • Customer name – Length validation • Mobile number – Length validation (mx 10 digit) • Email – email format validation • Address • City • Pin code – length validation Above all fields should be mandatory | done
| Fetch all customer | Use a Get service to fetch all customer details from db | done
| Verify the add customer service using postman. | Use different data set (Use valid & invalid inputs) | done
Product | Insert Some product details in db manually |  | done
Item Order | Create new order | Create a post service to add new order. 1. Validate input values 2. Insert order details to "ItemOrder" table. 3. Insert details to "TrackingDetails" table | working on it
| Order validation | Following fileds should be mandatory Customer id Product id Origin id Destination id Order status - It should be "New" when create new order | started
|  | Order date - Use current date | started
| Order status | Order status values are, 1. New 2. Shipped 3. Delivered 4. Canceled | started
Order Tracking | Insert details to "TrackingDetails" table | Create new entry with newly created "Order number" Initally the "Order status" should be "New" Last updated date - current date | not yet started
| Updated order status | 1. Create a POST service with the following inputs. - Order number - Status Both 2 fileds are mandatory - Last updated date - current date 2. Insert the these values in "TrackingDetails" table. 3. Update "OrderDetails" table with the following fields in curresponding order number, 1. Order status 2. order date | not yet started